## L0_Task List
SL.No | L0 Task List | Status | End Date
1 | Consolidation of existing projects arifacts for reference data. | Completed
2 | Feature List preparation for CBX FO -Account Services. | Completed
3 | Feature List preparation for CBX FO - Payments. | Completed
4 | Feature List preparation for CBX FO - Common Features. | Completed
5 | Feature List preparation for CBX FO - Liquidity. | Completed
6 | Feature List preparation for CBX FO- Collections and Receivables. | Completed
7 | Feature List preparation for CBX Back Office. | Completed
8 | Feature List preparation for Mobility - Account Services. | Completed
9 | Feature List preparation for Mobility - Payments. | Completed
10 | Feature List preparation for Mobility - Common Features. | Completed
11 | Feature List Preparation for Payments BO. | Completed
12 | Feature List Preparation for Cash Core. | Completed
13 | Feature List Preparation for Liquidity Back Office. | Completed
14 | Feature List Preparation for CnR Back Office. | Completed
15 | Feature List Preparation for Host 2 Host. | Completed
16 | Sharing the feature list with the cluser leads/SME's for Internal Review. | Completed
17 | Internal Discussions with the team/SME’s on the feature list prepared for CBX Account Services and to capture the addition features, if any. | In-Progress
18 | Internal Discussions with the team/SME’s on the feature list prepared for CBX Payments and to capture the addition features, if any. | In-Progress
19 | Internal Discussions with the team/SME’s on the feature list prepared for CBX Common Features and to capture the addition features, if any. | In-Progress
20 | Internal Discussions with the team/SME’s on the feature list prepared for CBX Liquidity and to capture the addition features, if any. | In-Progress
21 | Internal Discussions with the team/SME’s on the feature list prepared for CBX CnR and to capture the addition features, if any. | In-Progress
22 | Internal Discussions with the team/SME’s on the feature list prepared for CBX Back Office and to capture the addition features, if any. | In-Progress
23 | Internal Discussions with the team/SME’s on the feature list prepared for Mobility and to capture the addition features, if any. | In-Progress
24 | Internal Discussions with the team/SME’s on the feature list prepared for Payments BO and to capture the addition features, if any. | Planned
25 | Internal Discussions with the team/SME’s on the feature list prepared for Cash Core and to capture the addition features, if any. | Planned
26 | Internal Discussions with the team/SME’s on the feature list prepared for Liquidity BO and to capture the addition features, if any. | Planned
27 | Internal Discussions with the team/SME’s on the feature list prepared for CnR BO and to capture the addition features, if any. | Planned
28 | Internal Discussions with the team/SME’s on the feature list prepared for Host 2 Host and to capture the addition features, if any. | Planned
29 | Review Comments Incorporation | Partially-Completed
30 | Finalization of Feature List | Planned
31 | Fixing Thumb rule for L0 line items from Final Feature List | Planned
32 | L0 line items - to be pulled-out/prepared from the Feature list based on Thumb Rule. | Planned
33 | Aligning of L0 line items under respective Verticals. | Planned
34 | Naming convention Proposal. | Planned
35 | Naming convention Review. | Planned
36 | Naming convention Confirmation and Finalization. | Planned
37 | Naming Convention updation on L0. | Planned
38 | L0 line items confirmation with Product Owners - on xls along with Naming Convention | Planned
39 | Incorporation of comments from Product owners if any | Planned
40 | L0 Chiclet header identification and pattern | Planned
41 | Reviewing and confirmation of L0 Chiclet header and Pattern with Ranga/Padhu. | Planned
42 | Finalization of L0 xls sheet in chiclet format | Planned
43 | L0 PPT prepartion | Planned
44 | L0 PPT Review Ranga/Padhu | Planned
45 | Review Comments Incorporation | Planned
46 | Final Review and approval by Ranga/Padhu | Planned
47 | Review with Senior Managament | Planned
48 | Signoff from Senior Management | Planned
49 | DTB-M L0 PPT Publising | Planned

## RTM_Task List
S No. | RTM - Task List | Remarks | End Date
1 | RTM Template Preparation. | Completed
2 | RTM shared to cluster leads for review. | Completed
3 | Incorporation of Review comments with Team. | Planned
4 | Review of RTM Template with Ranga / Padhu. | Planned
5 | Product and Functional coverage Validation of RTM Template. | Planned
6 | Final Template for Review with Padhu/Ranga. | Planned
7 | Thumb rule to be fixed for deriving L1,L2 Items across Verticals. | Planned
8 | Legend to be prepared for filling up each and every column of the RTM with respect to Product and Functional Fields. | Planned
9 | Rules to be set as part of Legend in Amending/adding additional line items on to RTM Sheet. | Planned
10 | RTM Numbering - Plan and conclusion with Ranga/Padhu | Planned
11 | RTM preparation for CBX FO -Account Services. | Planned
12 | Country specific L0/L1/L2 items to be highlighted along with Country Name. | Planned
13 | Review with the Internal Team | Planned
14 | RTM preparation for CBX FO - Payments. | Planned
15 | Country specific L0/L1/L2 items to be highlighted along with Country Name. | Planned
16 | Review with the Internal Team | Planned
17 | RTM preparation for CBX FO - Common Features. | Planned
18 | Country specific L0/L1/L2 items to be highlighted along with Country Name. | Planned
19 | Review with the Internal Team. | Planned
20 | RTM preparation for CBX FO - Liquidity. | Planned
21 | Country specific L0/L1/L2 items to be highlighted along with Country Name. | Planned
22 | Review with the Internal Team | Planned
23 | RTM preparation for CBX FO- Collections and Receivables. | Planned
24 | Country specific L0/L1/L2 items to be highlighted along with Country Name. | Planned
25 | Review with the Internal Team | Planned
26 | RTM preparation for CBX Back Office. | Planned
27 | Country specific L0/L1/L2 items to be highlighted along with Country Name. | Planned
28 | Review with the Internal Team | Planned
29 | RTM preparation for Mobility - Account Services. | Planned
30 | Country specific L0/L1/L2 items to be highlighted along with Country Name. | Planned
31 | Review with the Internal Team | Planned
32 | RTM preparation for Mobility - Payments. | Planned
33 | Country specific L0/L1/L2 items to be highlighted along with Country Name. | Planned
34 | Review with the Internal Team | Planned
35 | RTM preparation for Mobility - Common Features. | Planned
36 | Country specific L0/L1/L2 items to be highlighted along with Country Name. | Planned
37 | Review with the Internal Team | Planned
38 | RTM Prepartion Cash Core. | Planned
39 | Country specific L0/L1/L2 items to be highlighted along with Country Name. | Planned
40 | Review with Team on the Cash Core line items | Planned
41 | RTM Preparation Payments. | Planned
42 | Country specific L0/L1/L2 items to be highlighted along with Country Name. | Planned
43 | Review with Team on the Payments line items | Planned
44 | RTM prepartion CnR. | Planned
45 | Country specific L0/L1/L2 items to be highlighted along with Country Name. | Planned
46 | Review with Team on the CnR line items | Planned
47 | RTM Preparation Liquidity. | Planned
48 | Country specific L0/L1/L2 items to be highlighted along with Country Name. | Planned
49 | Review with Team on the Liquidity line items | Planned
50 | RTM Preparation Host-Host. | Planned
51 | Country specific L0/L1/L2 items to be highlighted along with Country Name. | Planned
52 | Review with Team on the H-H line items | Planned
53 | Shared for review with Cluster Leads | Planned
54 | Review Comments Incorporation,If any. | Planned
55 | Final Review and approval by Ranga/Padhu | Planned
56 | Review Comments Incorporation,If any. | Planned
57 | Review with Senior Managament | Planned
58 | Review Comments Incorporation,If any. | Planned
59 | Signoff from Senior Management | Planned
60 | DTB-M RTM Publising | Planned
61 | Based on Final Template of RTM, other key fields to be filled up based on the completion of respective Artifacts like UJ, Ipad, etc | Planned